## Slide 1: Case-Level Database Phase II
Call 1 Monday, June 15th 2015

## Slide 2: Project timeline
Working Definition
Establish utility by
Identifying users
Feasibility Study
Identify and Address concerns
Implementation/
Logistics
α/β testing v1 release
Collect data and populate
= approx 1 month

## Slide 3: 1. Formal Definition Little progress
ILDB is still many things to many people
We need a formal, working definition that outlines:
  what it is, and how it is different from existing resources (kinds of queries: VUS? nearby variants? phenotype?)
  what problems it addresses (use-case list)
  what concerns it raises (IRB issues, consent)

## Slide 4: 2. Establish Utility Some progress
Cardio Clinical WG (done)
  Euan Ashley
  Current protocol for sharing patient data to solve VUS’s involves manually scrubbing PHI and collating on Excel sheets
Need more users (TBD)
  Verbal commitments not difficult to obtain
  feedback/feature requests

## Slide 5: 3. Feasibility Study Good progress
Do it ourselves vs. license a solution (done)
Solution provider bake-off (done)
  Gene Insight
  Ingenuity
  Cartegenia

## Slide 6: 4. Addressing Concerns Some progress
Privacy concerns
  Controlled vs. Anonymous access (specifics TBD)
  PHI scrubbed, but all phenotype/genotype shares (specifics TBD)
  Consent language for clinical samples already collected (specifics TBD)
Data Contributors/Users
  Partners LMM (verbal agreement)
  GeneDx, Invitae, Ambry others (outreach TBD)
  ClinGen clinical domain WGs (verbal agreement)
Operational concerns
  Getting locked in to GI as a provider (bulk downloads offered)
  IRB approval at hosting institution (host institution undecided)

## Slide 7: 5. ILDB Implementation Little progress
Implementation Aspect | Option 1 (>5X time) | Option 2 (>2X time) | Option 3 (1X time)
Hosting site | Stanford | Partners LMM | Partners LMM
Data-cleaning / populating DB | Stanford | Stanford | Stanford/ Partners LMM
Sys-admin / maintenance | Stanford | Stanford | Partners LMM
IRB institution | Stanford | Stanford/ Partners LMM | Partners LMM

## Slide 8: 6. Populate DB with patient records No progress
Data scrubbing protocol to be established
  Which fields stay, which get removed. Might differ lab to lab.
  Automated vs. manual scrubbing?
  Independent verification before upload?
Data contributors will most likely choose bulk-upload
  If @Stanford, HR to be identified/interviewed/hired
  If @PartnersLMM, fewer logistical requirements?

## Slide 9: 7. Going online No progress
End 2015 / Early 2016?

## Slide 10: Project timeline
Working Definition
Establish utility by
Identifying users
Feasibility Study
Identify and Address concerns
Implementation/
Logistics
α/β testing v1 release
Collect data and populate
= approx 1 month