## Slide 1: Case-Level Database Phase II
Call 2 Monday, July 20th 2015

## Slide 2: Project timeline
Working Definition
Establish utility by
Identifying users
Feasibility Study
Identify and Address concerns
Implementation/
Logistics
α/β testing v1 release
Collect data and populate
= approx 1 month

## Slide 3: 1. Formal Definition Little progress
Early version of manuscript being prepared that describes and motivates the ILDB

## Slide 4: 2. Establish Utility Some progress
Data sources: current verbal agreements
  Partners LMM (done)
  GeneDx?
  Invitae?
  Emory?
  Ambry (communication established)
ILDB Users
  Cardio Clinical WG, Euan Ashley (done)
  Noonan syndrome?
  Cancer?

## Slide 5: 5. ILDB Implementation Some progress
SaaS model finalized
  SunQuest/Partners hand-off
  Costs/licensing fees (need to be worked out)
IRB approval
  at whichever institution is administering usage and granting new users access (host institution undecided)
  approval contingent on having concrete processes in order
Meeting in Boston with technical staff from data contributors

## Slide 6: Project timeline
Working Definition
Establish utility by
Identifying users
Feasibility Study
Identify and Address concerns
Implementation/
Logistics
α/β testing v1 release
Collect data and populate
= approx 1 month